## HA Verification Checklist
No | System / Layer | Verification Area | Verification Item | Expected Result | Actual Result | Pass / Fail | Remarks | Evidence (Log / Screenshot)
1 | EBS41 | Access | Able to connect and log in to EBS41 | Login successful
2 | EBS41 | Network | EBS41 able to ping Wthost | Ping successful
3 | EBS41 | Data Ingress | Data transfer from Wthost to EBS41 | Transfer successful
4 | EBS41 | Data Replication | Data transfer from EBS41 to EBS42 | Transfer successful
5 | EBS41 | Network | EBS41 able to ping EBS42 | Ping successful
6 | EBS41 | Application Function | EBS41 able to perform lot aggregation | Completed successfully
7 | EBS41 | Application Service | EBS XE able to extract data | Extraction successful
8 | EBS41 | Integration | EBS XE able to receive XE request from ALF | Request processed
9 | EBS41 | HA Connectivity | Connect to BKGLV0038 (Primary) | Connection successful
10 | EBS41 | HA Connectivity | Connect to BKGLV0039 (Secondary) | Connection successful
11 | Database | DB Access | Connect to BKGLS0014 via EBS41 | Connection successful
12 | Database | DB Access | Connect to BKGLS0013 via EBS41 | Connection successful
13 | Database | Client Access | Connect to BKGLS0014 via Laptop | Connection successful
14 | Database | Client Access | Connect to BKGLS0013 via Laptop | Connection successful
15 | Database | HA Role | Verify Primary / Secondary roles | Roles correct
16 | Database | HA Health | No DB HA alert or replication lag | Normal status
17 | STEPP BE | Access | Able to connect and log in to STEPP BE | Login successful
18 | STEPP BE | Network | STEPP BE able to ping EBS42 | Ping successful
19 | STEPP BE | HA Connectivity | Connect to BKGLV0022 (Primary) | Connection successful
20 | STEPP BE | HA Connectivity | Connect to BKGLV0021 (Secondary) | Connection successful
21 | STEPP BE | Data Ingress | Data transfer from Orbit to STEPP | Transfer successful
22 | STEPP BE | Data Egress | Data transfer from STEPP to EBS42 | Transfer successful
23 | End-to-End | Functional Flow | Sample lot processed end-to-end | Completed successfully
24 | End-to-End | Data Integrity | No data loss or duplication | Data consistent
25 | End-to-End | Error Handling | No files stuck in bad / in_work / trigger | Clean state
26 | Monitoring | Alerting | No critical monitoring alerts | Normal status
27 | Performance | SLA | Response time within SLA | Within SLA
28 | HA Readiness | Failover | Service continues after failover | Service available
29 | HA Readiness | Role Switch | Primary/Secondary switch verified | Switch successful
30 | HA Readiness | Recovery | Services recover automatically | Recovery successful